## contributionreport
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Jamie Smart | Contributed to Quality Assurance Plan section | New court notifications, Subscription notifications, Notifications | N/A | Ran test cases, completed document | Created slides for and presented Quality Control section and Demo | Wrote the majority/entirety of ChangeUserCourtStatus.java, Court.java, Notification.java, ProximityChecker.java, service.java and part of User.java, fixed bugs across various filed | Did manual tests |  | Took meeting minutes for 2 meetings and put together format for final presentation
Duoyao Zhang | Contributed to Security section | Login feature, Firebase readtime database, Firebase User Authentication | N/A | Firebase authentication unit test Firebase database write test Firebase database read test | Created slides for App security and presented | Wrote the majority of FirebaseAuth.java, SignupActivity.java and part of User.java, Logout.java fixed bugs across various filed |  | Set up firebase realtime database, and firebase auth, Generated Firebase API key | Recorded 2 meetings and documented the meeting information
Sriram Ramdoss | Contributed to High Level Requirment | View all Courts and Subscribe option,List of users subscribed courts,user Subscribe option | Updated Database - Firebase | N/A | Created Slides for Requirement Anlysis and User stories and presentation for iteration 3 | Wrote to list all court in map and added marker,subscribetocourt |  | Setup firebase authentication and added firebase auth json in application | Recorded and documented meeting information
Saloni Rawat | Contributed to Management Plan and configuration plan | Email login ; creating tournament; edit user information | Controibuted to the introduction, android platform and database | wrote some basic unit testcases, ran test cases. | Created slides for project management | created the starting page, singup activity, worked on UI and navigation for the app |  | Setup firebase authentication | -created risk management - recorded 2 meetings
-

## MikeZhong
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/12-9/19 | 3 | 3 | 1 | 0 - set up android studio IDE and SDK 0 - complete android tutorial 1 - define high level user requirements 2 - consider designs | 3 | 1 | 1 | [5 empty] | 1. Author sections of SPPP 2. Set up git, commit a test message on git | 1. New tech stack and unfamiliar language
2 | 9/19-9/26 | 4 | 4 | 1 | 0 - learn the Android Play Services API 1 - write 3 user stories and acceptance tests | 2 | 2 | [6 empty] | 1. Read Android play services API documentation 2. Write user stories
3 | 9/26-10/3 | 3 | 3 | 1 | 3 - Implement fetching user location data and display to screen 5 - coordinate and organize tasks for other group members for next iteration |  |  |  | 2 |  | 1 |  |  | 1. Commit and push to user-location branch |  |  | Continue developing user location and proximity alert code
4 | 10/3-10/10 | 4 | 4 | 1 | 4 - Test location update by moving around outdoors 5 - manage deliverables and coordination of user location, notification, and user login tasks 0 - learn about android unit testing and instrumented testing | 1 | [7 empty] | 1. Merged all individual working branches 2. review notification code | 1. Need to draft UI design 2. Need to determine file based database usability 3. Need to integrate user location, user login, notification system, and known location for testing |  | Begin integration of firebase database with existing functional code
5 | 10/10-10/17 | 4 | 4 | 1 | 6 - merge individual working branches into dev 0 - learn about firebase 3 - added "locations" table to database | 2 |  |  | 1 |  |  | 1 |  | 1. All iteration 2 branches merged into dev 2. Review firebase configuration | 1. Need to better understand firebase database, where are the primary keys? 2. Need to understand Android ORM for accessing and manipulating database 3. Need to understand how Android handles database connections and sessions |  | Integrate firebase access and data manipulation into the user location code Integrate notifications
6 | 10/17-10/24 | 3 | 3 | 1 | 0 - continue learning about read/write to firebase from Android. Specifically how to handle larger queries from relation table type structures 2 - define life cycle of the application, listeners, call backs, and using composition of smaller objects to handle state 5 - do use case diagram and class diagram | 1 |  | 1 |  |  | 1 |  |  | 1. Use case diagram and class diagram | 1. Need to align with team on life cycle of the application and how to handle user state with respect to proximity. 2. Consider keeping court relation table and all court based notifications as optional features (difficult to implement without central server) |  | Start developing the heavy lifting classes which will handle onLocationChange() type activities. Integrate Jamie's code with table lookup into the user-relation table
7 | 10/24-10/31 | 2 | 2 | 1 | 5 - Coordinate individual development activities 6 - Manage git branches, commit history | [5 empty] | 1 | 1
8 | 10/31-11/7 | 5 | 5 | 3 | 3 - Work on AddCourtActivity 3 - Group work on various issues |  |  |  | 5 |  |  |  |  | 1. AddCourtActivity and associated layouts, manifest, and gradle additions are ready | 1. Need to add button that writes new court data to firebase |  | Complete the AddCourtActivity
9 | 11/7-11/14 | 10 | 5 | 5 | 3 - Work on SubscribeToScourtActivity 2 - Model event loop, system of callbacks 2 - Consider scoping of database operations and handling of asynchronous DB read/writes |  |  | 1 | 8 |  |  |  |  | 1. SubscribeToCourtActivity and associated layout, manifest, and gradle additions are ready 2. Completed implementation of AddCourtActivity, button is functional and DB write works and is tested | 1. Need to block adding courts to DB if a court name is already there 2. Reading courts from DB is async, how will I know when the read is complete? 3. How do I store data read from DB into local variables? Firebase seems to only allow the use of ValueEventListener and OnDataChange() callbacks 4. How do we pass the current user and list of users/courts from different activities |  | Complete SubScribeToCourtActivity. Finalize event loop in the landing page, inject logic for proximity checking, adding presentUser to the court DB, need to test that other users register the DB update and notify accordingly
10 | 11/14-11/21 | 8 | 3 | 5 | 3 - Complete implementation of SubscribeToCourtActivity 3 - Group work on various issues | [8 empty] | 1 . SubscribeToCourtActivity is fully functional and updates the user to reflect they are now subscribed to a given court 2. the courtsSubscribedTo field of the user gets updated but unsubscribing courts is still not ready 3. Decouple the view from the database by calling updateUI() in the listener's OnDataChange() method, asynchronous update of the UI to reflect real-time DB | 1. Courts that are subscribed do not have their marker color updated 2. Attempts to show all markers on the AddCourtActivity needs to implement the court that wants to be added as a different color or marker. Need to also not clear all markers when clicking a new location
11 | 11/21-11/28 | 12 | 12 | 0 | 3 - Implement the UserListView and UserAdaptors 3 - Implement populating the view and observer/observable pattern |  |  |  | 12 |  |  |  |  | 1. User List view is successfully implemented and follows observer/observable pattern 2. Users show up as adaptor items which are populated by reading the DB via listener, and calling updateUI() | 1. Need to implement sub/unsub user feature still 2. Need to check for each user whether or not they are currently subbed by the current user. This is not so trivial since we need to two listeners, one to read all users, and the other to read the current users userSubscribedTo field
12 | 11/28-12/5 | 2 | 2 | 0 | 5 - update slides for presentation, update SDD 2 - generate sequence diagrams for all use cases |  |  | 1 |  |  | 1 |  |  | 1. Finishing touches to SDD and powerpoint

## SaloniRawat
Lead Roles: Project Leader, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/12-9/19 | 2 | 2 | 0 | 0 - learn 0 - set up android studio IDE and SDK 0 - complete android tutorial 1 - define high level user requirements 2- consider designs | 1 | 1 | [6 empty] | 1. Edited team.md & meeting minutes 2. Updated deliverables for Phase 0 | 1. New tech stack and unfamiliar language
2 | 9/19-9/26 | 6 | 4 | 1 | 0- learn implementation of SQLite 1- define more details under user requirements 3- start developing a test login page 7- updated SPPP document | 2 | 1 | 2 |  |  |  |  | 1 | 1. Updated SPPP | 1
3 | 9/26-10/3 | 6.5 | 5.5 | 1 | 2- Updated Management plan under SPPP 2- Updated the SDD 5- defect metrics 6- Update project docs in Git |  |  | 3 |  |  | 2 | 0.5 |  | 1. Update management plan under SPPP 2. Started drafting SDD 3. Created defect tracker | 1. Project schedule details are missing. | Active 10/17: Closed, project schedule is up | 3 | 4
4 | 10/3 - 10/10 | 4.5 | 3.5 | 1 | 2- Update SDD and SPP 4- created test template 5- Create project schedule 5- updated risk management |  |  | 1 |  | 0.5 | 2 |  |  | 1. SPPP, SDD are up to date 2. Tentative project schedule is up 3. Risk management updated | 1. Delay in testing | Active; to create a GUI test plan and unit test script 10/17: created a GUI test plan; working on functional test script. | 4
5 | 10/10 - 10/17 | 6.5 | 5.5 | 1 | 0- Research on UI automator and Junit 4- Perform Testing on FB login and User location 4- update unit test document 5 - update SDD and risk management docs 5- Slack communication 6- Update project docs in Git | 1 |  |  |  | 2 | 2 | 0.5 |  | 1. 2 new defects in defect tracker 2. unit test on FB login | 1. unclear on how the app will flow. 2. Undefined testcases. | 1. Storyboard for the remaining classes. 2. follow up on the test cases. | 5
6 | 10/17-10/24 | 3 | 2 | 1 | 4 - Perform Testing on FB login and user location 4 - create all test cases/script |  |  |  |  | 2
7 | 10/24-10/31 | 2 | 2 | 1 | 3- user interface 4- test UI elements |  |  |  | 1 | 1
8 | 10/31-11/7 | 5 | 2 | 3 | 3- Design the layout for the remaining pages 3- Display the court and subscriber data |  |  |  | 5 |  |  |  |  | 1. Developed UI for the starting page, home page, courtList activity | currently hardcoded data. | Need to work on pulling the data from the db and display to the list | 3
9 | 11/7-11/14 | 4 | 1 | 3 | 3 - Storing user info in the Authentication db and Realtime DB 3- Created myaccount with logout. 3- Multi-navigation page for android page to view map view of the courts, subscriber list view and account info. |  |  |  | 4 |  |  |  |  | 1. Developed UI for the court and subscriber list view, my account 2. Storing user information using firebase and storing imp user info on the database | 1. unable to store the db info in the app in a list form to be used later 2. Some user information such as phno. not being stored in DB |  | 4
10 | 11/14-11/21 | 10 | 5 | 5 | 3- pull info from DB 3- work on UI elements 3- display users and subscriber relation |  |  |  | 5 |  |  |  |  | 1. created the | 1. unable to pull the data in the recycler view since it is async
11 | 11/21-11/28 | 4 | 4 | 0 | 3- display users and subscriber relation 4- perform basic testing |  |  |  | 2 | 2
12 | 11/28-12/5 | 5 | 5 | 0 | 6- updated documentation 6- work on final presentation | [6 empty] | 5 |  | 1. Updated the risk management

## JamieSmart
Lead Roles: QA Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/12-9/19 | 3 | 2 | 1 | 0 - learn 0 - set up android studio IDE and SDK 0 - complete android tutorial 1 - define high level user requirements 2 - consider designs | 0 |  |  |  |  | 1
2 | 9/20-9/26 | 5 | 4 | 1 | 0 - learning about android notifications | 4 |  |  |  |  | 1
3 | 9/27-10/3 | 7 | 6 | 1 | 1 - requirement analysis to develop user stories 2 - basic app design 3 - continue implementation of general notification feature 5 - project discussion / meeting |  | 1 | 1 | 4 |  | 1 |  |  | notifications almost finished | None |  | finish general notification setup | 2h
4 | 10/4-10/10 | 8 | 7 | 1 | 3 - work on implementing android notifications |  |  |  | 7 | [7 empty] | Continue to work on Firebase notifications
5 | 10/11-10/17 | 5.5 | 5 | 0.5 | 3 - work on implementing android notifications 5 - Slack communication |  |  |  | 4 |  | 1 |  |  | text notifications | Unable to implement Firebase messaging |  | Reattempt Firebase notifications with Duoyao's Firebase Project, work on court database | 8
6 | 10/18-10/24 | 3 | 2 | 1 | 0 - learn about Firebase NoSQL databases | 2 | [10 empty] | Implement Courts database | 2
7 | 10/25-10/31 | 3.5 | 3 | 0.5 | 3 - set up Courts database and ability to read from database |  |  |  | 3 |  |  |  |  | Courts database updated and access implemented |  |  | Testing current code | 2
8 | 10/31-11/7 | 6 | 3 | 3 | 3 - set up notification sending |  |  |  | 6 |  |  |  |  | Set up push notification capabilities |  |  | Make tweaks
9 | 11/8-11/14 | 7 | 2.5 | 4.5 | 3 - add Court class features |  |  |  | 7 |  |  |  |  | Make tweaks |  |  | Work on Subscription features
10 | 11/15-11/21 | 5 | 3 | 2 | 3 - bug fixes |  |  |  | 3 |  |  |  |  | Fixed bugs |  |  | Testing current code | 2
11 | 11/22-11/28 | 8 | 8 |  | 3 - set up service |  |  |  | 8 | [7 empty] | Figure out a way for app to continunuously work in background | 4
12 | 11/29-12/5 | 7 | 7 |  | 3 - bug fixes 4 - test service 7 - work on presentation |  |  |  | 5 | 2 |  |  |  | created service that checks user proximity to courts and sends notifications, fixed bugs |  |  | Cleaning up project

## Sriram
Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/12 - 9/19 | 3 | 2 | 1 | 0 - learn 0 - set up android studio IDE and SDK 0 - complete android tutorial | 3 | [8 empty] | 1. New tech stack and unfamiliar language
2 | 9/20 - 9/26 | 2 | 2 | 0 | 0 - learning android studio and SQLite connectivity | 2
3 | 9/27 - 10/03 | 5 | 4 | 1 | 1 - requirement analysis to define user stories 2 - design basic login page and connectivity to SQLite 5 - project discussion with team 7 - updated SPPP document |  | 1.5 | 1 |  |  | 1 |  | 1.5 | 1. Updated SPPP | 1. Configuration error on SQLite | 1. Reinstall and trying connectivity
4 | 10/03 - 10/10 | 2 | 1 | 1 | 0 - Tutorial about Firebase | 1
5 | 10/10 - 10/17 | 6 | 5 | 1 | 6 - Connecting Android studio application and Firebase project (Manually) 6 - Enabled Facebook Login authentication in firebase by generating Hash key 7 - updated SDD document" | [6 empty] | 4.5 | 0.5 | 1.Updated SDD Document | 1.connection not established between application and firebase 2.Authentication user enable | 1. connected manually by adding json file in app 2 - Enabled by generating projectID in facebook developer | 1.Want to get user information from social login and to be stored in firebase
6 | 10/17-10/24 | 3 | 2 | 1 | 0- Learning about non SQLFirebase DB 5- project discussion with team | 2 |  |  |  |  | 1
7 | 10/24-10/31 | 3 | 2 | 1 | 0- Learning about non SQLFirebase connectivity by using json 5- project discussion with team | 2 |  |  |  |  | 1
8 | 10/31-11/7 | 3 |  | 3 | 3 - worked on the AddCourtActivity, implemented basic map overlay to display all courts |  |  |  | 3 | [7 empty] | work on user subscribetocourt
9 | 11/7-11/14 | 4 |  | 1 | 3- worked on layout alignment and in subscribe to court page |  |  |  | 3
10 | 11/15-11/21 | 2 |  |  | 3-performing data retrive from real time database |  |  |  | 2
11 | 11/22-11/28 | 2 |  |  | 3-Bug fixing |  |  |  | 2
12 | 11/29-12/5 | 3 |  |  | 4- test app features 7-work on presentation |  |  |  |  | 1.5 |  |  | 1.5 |  |  |  | project delivery and github merge

## Duoyao Zhang
Lead Roles: Security Leader, UI Design
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/12-9/19 | 3 | 3 | 1 | 0 - learn 0 - set up android studio IDE and SDK 0 - complete android tutorial 1 - define high level user requirements 2 - consider designs | 2 | 1 | 1 | [5 empty] | 1.Set up git, slack, pivot tracker and Android studio 2. Commit my information on github for Lab1 | 1. Not familiar with Kotlin language |  | 1. Build a useable GUI sample
2 | 9/19-9/26 | 3 | 2.5 | 0.5 | 0 - Created a user story about login with facebook/google account 1 - Start working on the functionality 2 - Created a webpage about the project | 0.5 | 1.5 | 0.5 | [5 empty] | Started working on the user login functionality | Not familiar with document dependencies
3 | 9/27-10/03 | 4.5 | 3.5 | 1 | 2 - Started a UI design 3- Implemented the facebook login feature | 2.5 | 1
4 | 10/4-10/10 | 6 | 5 | 1 | 3 - work on User registration from firebase database 4 - read and write user sign up information from firebase realtime database |  |  |  | 2.5 | 2.5 | [6 empty] | Continue to work on Firebase realtime database
5 | 10/11-10/17 | 6 | 5.5 | 0.5 | 2 - work on landing page, homepage's UI design 3 - work on user authentication from firebase database |  |  | 2 | 3.5 |  | 1 |  |  | User signup information viewable on firebase console | Unable to implement Firebase authentication |  | implement firebase authentication and user email patterns detection | 8
6 | 10/18-10/24 | 6 | 5 | 1 | 3- implement the firebase authentication
7 | 10/25-11/2 | 8 | 4 | 4 | 3- completed implementation on firebase authentication 4- tested firebase authentication |  |  |  | 3 | 5 |  |  |  | Firebase can authenticate user with registrated account number with according password. Instead of writing user password directly into the app account database. Now firebase authentication seperatedly store user password in the secure database and user password is not directly exposed to the App administrater. | User couldn't logout the app once they got logged in |  |  | 4
8 | 11/3-11/10 | 6.5 | 2 | 4.5 | 3 - Logout button 4 - Tested whole login and logout work flow |  |  |  | 3.5 | 3 | [7 empty] | 5
9 | 11/11 - 11/21 | 6 | 2 | 4 | 3- Write user data in realtime database 4- Database read/write test |  |  |  | 2 | 4 | [7 empty] | 4
10 | 11/22 -11/28 | 6 | 2 | 4 | 3= group work on proximity and addUser, Addcourt feature |  |  |  | 6 | [8 empty] | 4
11 | 11/29-12/5 | 6 | 3 | 3 | 3 - bug fixes 4 - test app features 7 - work on presentation |  |  |  | 2 | 2 |  |  | 2 |  |  |  | Project delivery Github merge | 4

## Metrics-GroupIterationProgress
iteration | Date range | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks
0 | 09/06-09/20 | 0 | 0 | 0 | 0 | 0 | 14 | 13 | 1 | 9 | 3 | 2 | 0 | 0 | 1 | 0
1 | 09/20 - 10/4 | 0 | 3 | 0 | 0 | 0 | 32 | 30 | 2 | 11 | 6 | 7.5 | 0 | 0 | 5 | 0.5
2 | 10/4-10/17 | 2 | 2 | 2 | 0 | 2 | 45 | 43 | 2 | 5 | 0 | 3 | 18 | 5 | 6 | 6
3 | 10/17 - 10/31 | 3 | 1 | 2 | 2 | 0 | 30 | 30 | 2 | 7 | 0 | 1 | 7 | 8 | 4 | 1
4 | 10/31-11/14 | 4 | 3 | 2 |  |  | 66.5 | 60.5 | 6 | 0 | 0 | 1 | 46.5 | 7 | 0 | 0
5 | 11/14 - 12/5 | 7 | 1 | 3 |  |  | 71.5 | 66.5 | 5 | 0 | 0 | 1 | 47 | 7.5 | 1 | 5

## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan
0 | 09/06-09/20 | 1. Kick off meeting and finalised the project - HoopFinder 2. The team worked on setting up and getting familarized with AndroidSDK and Android Studio. 3. High level requirements finalized 4. Worked on Lab1. |  | - unfamiliar with AndroidSDK | - Everyone to research and follow android tutorials
1 | 09/20-10/4 | 1. User requirements defined 2. Development work in progress: - Can pull user location information - can display notifications - Email and Facebook login. 3. SPPP completed 4. Drafting SDD | 1. Facing issues with integration with SQLite 2. Possible to store unique identifier for the facebook to identify user 3. Decide between using android vs. androidx imports |  | 1.looked up tutorial on Android developers, follow the details provided. 2. Research facebook API to identify the key, find a way to store in DB 3. Finalize organization of project classes 4. Decide how to handle users leaving a court after a notification is sent
2 | 10/4 - 10/17 | 1. User requirement refined 2. Completed: - facebook login completed. - user data stored on database - court location table created - text messages enabled. 3. Updated SDD, risk management. 4. Testing started; test case template and defect tracker. | 1. Faced issues trying to integrate Firebase 2. Retrieveing phone number from Fb | - unfamiliar with Junit testing and TestLab | 1. Come up with UI flow 2. Create a database architecture 3. Research Firebase to check notifications
3 | 10/17- 10/31 | 1. Completed: - add and manage courts info on DB - user subbscrider table created - UI for the displaying user and courts info - display courts on map view | 1. Facing issues to add new markers to map view 2. Currently since we are storing fb info, we are unable to attach a session to user and retrieve relative info from the user. | - unable to test the full application since all pages are not connected. | 1. To create a consolidated UI for testing 2. To work more on integrating the db tables
4 | 10/31 -11/14 | 1. Completed: - UI for subscriber info; court info - Logout for user - Add and view courts on the map view - custom user login using credentials - associating session with UID. 2. Updated SPPP and SDD; risk management | 1. Facing issues storing related user info in DB
5 | 11/14 - 12/5 | 1. Updated SPPP, SDD, STD; risk management; test documents 2. creatdd demo video for final presentation 3. created final video slides